## Bugs
Bug ID | Module | Summary | Precondition / Prerequisite | Steps to Reproduce | Expected Result | Actual Result | Severity | Status | Repro Video
BUG_01 | Checkout | Empty Cart Order Place | User should have valid Username and valid Password credentials User should NOT have added any product to the Cart | Step 1 : Open this https://www.demoblaze.com/ in a browser. Step 2 : Click on "Log in" option top right. Step 3 : Enter valid username under 'Username' field. Step 4 : Enter valid password under 'Password' field. Step 5 : Click on "Log in" button and get login successfully. Step 6 : Click on "Cart" option from top. Step 7 : Click on "Place Order" option. Step 8 : Enter the details in the form. Step 9 : Click on "Purchase" button from bottom and Observe. | Verify that the User should NOT be able to place the order with empty cart. | User get the confirmation message as "Thank you for your purchase" | HIGH | OPEN
BUG_02 | Categories | Category Navigation (Laptops/Phones/Monitors) | User should have valid Username and valid Password credentials | Step 1 : Open this https://www.demoblaze.com/ in a browser. Step 2 : Click on "Log in" option top right. Step 3 : Enter valid username under 'Username' field. Step 4 : Enter valid password under 'Password' field. Step 5 : Click on "Log in" button and get login successfully. Step 6 : Click "Laptops/Phones/Monitors" option from left side menu under 'Categories' section and Observe. | Verify that the perticular procuct category should be shown as selected from left side menu. | User is NOT able to see the product category as selected. | MED | OPEN
BUG_03 | Product | Product Selection Failed | User should have valid Username and valid Password credentials | Step 1 : Open this https://www.demoblaze.com/ in a browser. Step 2 : Click on "Log in" option top right. Step 3 : Enter valid username under 'Username' field. Step 4 : Enter valid password under 'Password' field. Step 5 : Click on "Log in" button and get login successfully. Step 6 : Scroll down and Click on "Next" option. Step 7 : Click on any "Laptop/Monitor" (Click on product thumbnail) and Observe. | Verify that the User should be able to open the product successfully. | User is NOT able to open/select the product. | HIGH | OPEN
BUG_04 | Product Gallery | Product image slider navigation failed | User should have valid Username and valid Password credentials | Step 1 : Open this https://www.demoblaze.com/ in a browser. Step 2 : Click on "Log in" option top right. Step 3 : Enter valid username under 'Username' field. Step 4 : Enter valid password under 'Password' field. Step 5 : Click on "Log in" button. Step 6 : Click on "Phones" option from left side menu under 'Categories' section Step 7 : Click on any phone from the list Step 8 : Click on image slider below product thumbnail and Observe. | Verify that user should be able to see all photos of product. | User is not able to see all photos of product. | LOW | OPEN
BUG_05 | Product Banner | Non-Responsive product homepage banner. | User should have valid Username and valid Password credentials | Step 1 : Open this https://www.demoblaze.com/ in a browser. Step 2 : Click on "Log in" option top right. Step 3 : Enter valid username under 'Username' field. Step 4 : Enter valid password under 'Password' field. Step 5 : Click on "Log in" button. Step 6 : Click on any product banner from homepage and Observe. | Verify that user should be able to view the product from homepage banner. | User is NOT able to see the product form homapage. | HIGH | OPEN
BUG_06 | Product Page | Homepage Navigation back. | User should have valid Username and valid Password credentials | Step 1 : Open this https://www.demoblaze.com/ in a browser. Step 2 : Click on "Log in" option top right. Step 3 : Enter valid username under 'Username' field. Step 4 : Enter valid password under 'Password' field. Step 5 : Click on "Log in" button. Step 6 : Scroll down on homepage and Click on "Next" button and refresh the page and Observe. | Verify that user should be able to view the current product page after refresh. | User is navigating back to homepage after refreshing the current/last page. | MED | OPEN